## WIN 8 OS Updates
TOEM | Code Name | Availability Date | LeadExit | TestApprove | Stretch TA | Active | Devices_Updated | Success Rate | Update Mechanism | Size_MB | SMS Notification Date | OS Ver Status | Device_Active_As
LG | Thunder | 2012-02-09 | 2011-10-03 | 2012-02-02 | 2012-02-02 | 154689 | 9922 | 6.414% | Sizeload | 117 | 0.22222 | Launched | 2012-11-15
LG | Cosmo | 2012-03-23 | 2011-10-17 | 2012-03-20 | 2012-03-20 | 189569 | 17673 | 9.323% | Sizeload | 400 | 2012-06-04 | Launched | 2012-11-15
Nokia | Moon | 2012-04-05 | 2012-01-16 | 2012-03-28 | 2012-03-28 | 140329 | 239 | 0.1703% | Sizeload | 224 | 2012-06-01 | Launched | 2012-11-15
Nokia | Vegas | 2012-01-10 | 2011-11-14 | 2011-12-16 | 2011-12-16 | 531886 | 49256 | 9.261% | Sizeload | 250 | 2012-02-05 | Launched | 2012-11-15
Samsung | Dempsey | 2012-04-04 | 2012-03-05 | 2012-03-29 | 2012-03-29 | 633389 | 46447 | 7.333% | Sizeload | 305 |  | Launched | 2012-11-15

## JET Campaigns
TOEM | Code Name | MR/ MRS | MR Type | LeadExit | TestApprove | Status | Availability Date | Push_Date | Update Mechanism | Zero Rated | Size_MB | Device Initated Query | Quality Board Review | Active | Devices_Pushed | Devices_Updated | Comments
LG | J1 | EMR2 | EMR2 | 2012-12-03 | 2012-12-17 | In Planning | 2012-12-19 | 2012-12-19 | RAN JET | Yes | 18 | Yes |  | 7754000 | 0 | 0
LG | Comanche | JB OS MR | MR | 2012-10-29 | 2012-12-12 | In Planning | 2013-01-01 | 2013-01-01 | RAN JET Wi-Fi | Yes | 405 |  |  | 17217000 | 0 | 0
Nokia | Expresso | JB OS MR | MR | 2013-01-14 | 2013-03-04 | In Planning | 2013-03-06 | 2013-03-06 | RAN JET Wi-Fi | Yes | TBD |  |  | 6146000 | 0 | 0
Nokia | Luna | EMR-APN | EMR | 2012-06-18 | DFD | In Planning | TBD | TBD | RAN JET | Yes | TBD | Yes | N/A | 62735000 | 0 | 0
Nokia | Juniper | EMR | EMR | 2012-11-19 | 2012-12-03 | In Planning | TBD | TBD | MSFT OTA |  |  |  |  | 12814000
Samsung | Prodigy | EMR | EMR | 2012-11-19 | 2012-12-03 | In Planning | TBD | TBD | MSFT OTA |  |  |  |  | 81093000
Samsung | ACDC | EMR | EMR | 2012-11-19 | 2012-12-03 | In Planning | TBD | TBD | MSFT OTA |  |  |  |  | 8793000
Samsung | Sapphire | MR CIQ | MR | TBD | TBD | In Planning | TBD | TBD | RAN JET | Yes | TBD | Yes | Review | 250368000 | 0 | 0
Samsung | Presto | EMR3 - CIQ | EMR | TBD | TBD | In Planning | TBD | TBD | RAN JET | Yes | TBD | Yes | Review | 357354000 | 0 | 0
Samsung | Mini | EMR1- CIQ | EMR | TBD | TBD | In Planning | TBD | TBD | RAN JET | Yes | TBD | Yes | Review | 47700000 | 0 | 0
Samsung | Lydian | CIQ EMR2 | EMR | TBD | TBD | In Planning | TBD | TBD | RAN JET | Yes | TBD | Yes | Review | 368910000 | 0 | 0
Samsung | Revere | EMR1- CIQ | EMR | TBD | TBD | In Planning | TBD | TBD | RAN JET | Yes | TBD | Yes | Review | 987360000 | 0 | 0
Samsung | Link2 | CIQ EMR2 | EMR | TBD | TBD | In Planning | TBD | TBD | RAN JET | Yes | TBD | Yes | 2012-03-08 | 316536000 | 0 | 0
Samsung | Auger | EMR-APN | EMR | TBD | TBD | In Planning | TBD | TBD | RAN JET | Yes | TBD | TBD | N/A | 135996000 | 0 | 0

## 2012 Sum
TOEM | Code Name | Month | Pushed | Updated | Platform | Size_MB | OS
LG |  | 2012-02-25 | 111625 | 92015 | RAN JET | 5 | WIN 8
LG |  | 2012-04-30 | 38839 | 31767 | RAN JET | 25 | WIN 8
LG |  | 2012-02-25 | 188117 | 6088 | Sizeload | 117 | WIN 8 OS - Gbread
LG |  | 2012-03-30 | 216996 | 12370 | Sizeload | 400 | WIN 8 OS - Gbread
LG |  | June |  |  |  |  | WIN 8 OS - EICS
LG |  | 2011-01-30 | 34590 | 29274 | RAN- Innopath | 1
LG |  | 2011-06-30 | 21198 | 16422 | RAN JET | 5
LG |  | 2010-07-30 | 15370 | 9087 | RAN JET
Nokia |  | 2012-04-30 | 26361 | 11234 | RAN JET | 18 | WIN 8
Nokia |  | 2012-02-25 | 239047 | 150366 | RAN JET | 5 | WIN 8
Nokia |  | 2012-06-30 |  |  |  |  | WIN 8
Nokia |  | 2012-04-30 | 144966 | 13050 | Sizeload | 224 | WIN 8 OS - Gbread
Nokia |  | August |  |  |  |  | WIN 8 OS - EICS
Nokia |  | September |  |  |  |  | WIN 8 OS - EICS
Nokia |  | 2012-04-30 | 81305 | 80716 | RAN JET | 13 | WIN 8
Samsung | Seine | 2012-01-30 | 384046 | 337183 | RAN JET | 19.5 | WIN 8
Samsung | Skyrocket | 2012-04-30 | 391359 | 326375 | RAN JET | 20 | WIN 8
Samsung |  | 2012-06-30 | 4565 | 4499 | RAN JET | 1 | WIN 8
Samsung | [6 empty] | WIN 8
Samsung |  | 2012-01-30 | 823398 | 120096 | Sizeload - Mini Kies | 250 | WIN 8 OS - Gbread
Samsung |  | 2012-04-30 | 738553 | 17265 | Sizeload - Mini Kies | 305 | WIN 8 OS - Gbread
Samsung |  | May |  |  |  |  | WIN 8 OS - EICS
Samsung | Skyrocket | June |  |  |  |  | WIN 8 OS - EICS
Samsung |  | June |  |  |  |  | WIN 8 OS - EICS
Samsung |  | August |  |  |  |  | WIN 8 OS - EICS
Samsung |  | September |  |  |  |  | WIN 8 OS - EICS
Samsung | Glide | September |  |  |  |  | WIN 8 OS - EICS
Samsung |  | 2011-06-30 | 98949 | 89657 | RAN JET | 8
Samsung |  | 2011-09-30 | 329349 | 243342 | RAN JET | 16
Samsung |  | 2011-09-30 | 279486 | 237581 | RAN JET | 1
Samsung |  | 2011-09-30 | 302042 | 221416 | RAN JET | 1
Samsung | GS2 | 2011-12-20 | 31411 | 24892 | RAN JET | 1
Samsung | Willow | 2012-01-30 | 47958 | 38117 | RAN JET | 8.5 | WIN 8
Samsung |  | 2012-06-30 |  |  |  |  | WIN 8
Samsung |  | 2010-10-30 | 284468 | 225340 | RAN JET